## TechnicalOnboarding_New
SN | Task | Performed by | Organization | Duration | Targeted Start Date | Targeted End Date | Actual Start Date | Actual End Date | Hub Remarks | Payment Manager Remarks | DFSP Remarks | Automation
Business Agreement to Proceed
1 | Staging - Engage DFSP
1.1 | Request/Provide the required APIs from DFSP/Get API collections from DFSP (CBS) with sample data and try out APIs | Ingyin,Sitt Oo | PM Saas Provider
1.2 | Gather Integration specification (DFSP business workflow and learn CBS) | Ingyin,Sitt Oo | PM Saas Provider
1.3 | Request logo from MFI | Ingyin,Sitt Oo | PM Saas Provider
1.4 | Engage DFSP to request the liquidity account number | Ingyin,Sitt Oo | PM Saas Provider
1.5 | Request the required credentials | Ingyin,Sitt Oo | PM Saas Provider
1.6 | Check the password expiration in CBS (or) API | Ingyin,Sitt Oo | PM Saas Provider
1.7 | Create Integration specification document (workflow+mapping) and get a sign off | Ingyin,Sitt Oo | PM Saas Provider
2 | Staging - Development between DFSP and Core Connector/Payment Manager
2.1 | Conduct feasiblity and mapping excercise with Dev team | Ingyin,Sitt Oo | PM Saas Provider
2.2 | CoreConnector development (loan repayment/disbursement) | Ko Myo
2.3 | Create the release version after development and provide to Dev ops | Ko Myo
2.4 | Run the core-connector locally and test, need to build core-connector requests based on its swagger (I’ll share some previous one we can use as a start)
3 | Staging - Register DFSP
3.1 | OAuth token generation | Pete | DFSP & Hub Operator
3.2 | Register DFSP Prefix in MFI Oracle | Pete | DFSP & Hub Operator
4 | Staging - Deploy Payment Manager
4.1 | Deploy PM4ML hosted instance that include core connector | Juan | PM Saas Provider
5 | Staging - Engage DFSP for PM4ML
5.1 | Engage DFSP to create PM4ML accounts, share initial credentials, verify 2FA set up | Ingyin,Sitt Oo | PM Saas Provider
5.2 | Engage DFSP to demo PM4ML UIs | Ingyin,Sitt Oo | PM Saas Provider
6 | Staging - Payment Manager Onboarding on MCM
6.1 | Add DFSP | Pete | DFSP & PM Saas Provider
6.2 | Add Public IP address of DFSP | Pete | DFSP & PM Saas Provider
6.3 | Sign DFSP Cert | Pete | DFSP & PM Saas Provider
6.4 | Onboard DFSP | Pete | DFSP & PM Saas Provider
7 | Staging - One sided/integrated testing between DFSP, PM and Hub
7.1 | Integrated testing between DFSP system and Core Connector | Ingyin,Sitt Oo & Dev | DFSP, PM Saas Provider & Mifos
8 | Staging - End-to-end integration testing between DFSP, PM and Hub
8.1 | End-to-end testing between DFSP systems and Core Connector and Hub | Ingyin,Sitt Oo & DFSP | DFSP, PM Saas Provider, Hub Op
9 | Prod - Engage DFSP
9.1 | Request the required credentials
9.2 | Check the password expiration in CBS (or) API
9.3 | Request the liquidity account number
10 | Prod - Payment Manager Deployment
10.1 | Deploy PM4ML hosted instance with simulated backend | Juan | PM Saas Provider
10.2 | OAuth token generation | Pete | DFSP & PM Saas Provider
10.3 | TLS client Certificate Signing Request (CSR) exchange and configuration | Pete | DFSP & PM Saas Provider
10.4 | TLS client CA chain exchange and configuration | Pete | DFSP & PM Saas Provider
10.5 | TLS server certificate exchange and configuration | Pete | DFSP & PM Saas Provider
10.6 | JWS certificate (public key) exchange and configuration | Pete | DFSP & PM Saas Provider
10.7 | Configuration of additional security settings | Pete | DFSP & PM Saas Provider
10.8 | Public IP address / callback URL exchange and setup | Pete | DFSP & PM Saas Provider
10.9 | Configuration of non-security settings | Pete | DFSP & PM Saas Provider
11 | Prod - Register DFSP in hub to establish DFSP ID
11.1 | Pre-Prod -Register DFSP in hub to establish DFSP ID | Pete | DFSP & Hub Operator
11.2 | Pre-Prod - Register DFSP Prefix in MFI Oracle | Pete | DFSP & Hub Operator
11.3 | Register Liquidity Account of DFSP in hub to show that account in settlement bank initiation report Later liquidity account registeration will be in finance portal | Wint Ei and MBX
11.4 | Check the liquidity and NDC in finance portal for new DFSP
12 | Prod - Set Up Wire guard
12.1 | DFSP VPN Tunnel (CBS to pm4ml) established and tested | Ingyin,Sitt Oo, Pete | DFSP & PM Saas Provider
13 | Prod - Engage DFSP after PM Deployment
13.1 | Engage DFSP to create PM4ML accounts, share intital credentials, verify 2FA set up | Ingyin,Sitt Oo | PM Saas Provider
14 | Prod - Connection between DFSP and Core Connector/Payment Manager
14.1 | CoreConnector deployment (Helm) | Ko Myo | PM Saas Provider
14.2 | (Temp) Access to Hub (simulator apis and credentials)
15 | Prod - Testing in production with test transactions (MFI provided API and CC getParty call) | BA, Hub Op | DFSP & PM Saas Provider, Hub Op
16 | Prod - Sign off | Ingyin,Sitt Oo | DFSP
17 | Go Live
Note: In Mobile Wallet go-live process, need to inform MFIs to add the payment method if they wish to do business with the new wallet, and to update the mapping in core connector.
Ingyin,Sitt Oo - role of PM Saas Provider and Project Management
Juan - role of Modusbox
Note: In Mobile Wallet go-live process, need to inform MFIs to add the payment method if they wish to do business with the new wallet, and to update the mapping in core connector.

## Definitions
Status
Waiting for DFSP
Waiting for Vendor
Waiting for Modusbox
Waiting for Payment Manager
Waiting for Hub
In Progress
Done
Not Yet started